## Jira Backlog
Issue ID | Issue Type | Summary | Description | Priority | Story Points | Sprint | Assigned To | Status
PD-0 | Epic | Plant Disease Detection Web App | Develop an AI-powered web app to detect plant diseases from leaf images. | High |  | Sprint 1-4 | Project Manager - Bijay Sharma | To Do
PD-1 | Story | Documentaton | Create SRS, Backlogs for jira, PPT, Final Report | High | 3 | Sprint 1 | Documentation-Ayush Bhardwaj | To Do
PD-2 | Story | Setup Flask Project Structure | Initialize Flask project with folder structure and base configuration. | High | 3 | Sprint 1 | Backend Dev - Pragyansh Dixit | To Do
PD-3 | Story | Implement Image Upload Feature | Allow users to upload JPG/PNG plant leaf images. | High | 5 | Sprint 1 | Frontend Dev - Ayush Bhardwaj | To Do
PD-4 | Story | Image Preprocessing Module | Resize images to 224x224 and normalize before prediction. | High | 5 | Sprint 1 | ML Engineer - Bijay Sharma | To Do
PD-5 | Story | Integrate Pretrained ResNet/MobileNet Model | Load and fine-tune transfer learning model for plant disease detection. | High | 8 | Sprint 2 | ML Engineer - Pragyansh Dixit | To Do
PD-6 | Story | Display Prediction Results with Confidence Score | Show predicted disease label and probability score on UI. | Medium | 5 | Sprint 2 | Frontend Dev - Ayush Bhardwaj | To Do
PD-7 | Story | Add Treatment & Prevention Suggestions | Display disease-specific treatment recommendations. | Medium | 3 | Sprint 2 | Backend Dev - Vaishnavi Shukla | To Do
PD-8 | Story | MongoDB Integration | Store image metadata and prediction results in MongoDB. | High | 8 | Sprint 3 | Backend Dev - Pushpendra Gangwar | To Do
PD-9 | Story | Prediction History Dashboard | Allow users to view previous predictions with timestamps. | Medium | 5 | Sprint 3 | Frontend Dev - Ayush Bhardwaj | To Do
PD-10 | Story | User Authentication (Optional) | Implement login/signup functionality for users. | Low | 5 | Sprint 3 | Backend Dev - Vaishnavi Shukla | To Do
PD-11 | Story | Model Performance Evaluation | Evaluate model accuracy, precision, recall and optimize. | Medium | 5 | Sprint 4 | ML Engineer - Bijay Sharma | To Do
PD-12 | Story | Cloud Deployment (AWS/Heroku) | Deploy Flask app with MongoDB Atlas support. | High | 8 | Sprint 4 | DevOps - Pragyansh Dixit | To Do
PD-13 | Task | UI Styling with HTML/CSS | Improve UI for better usability and responsiveness. | Medium | 3 | Sprint 2 | Frontend Dev - Ayush Bhardwaj | To Do
PD-14 | Task | Testing & Bug Fixing | Perform functional and integration testing. | High | 5 | Sprint 4 | Qas - Pushpendra Gangwar | To Do